## Overview (hidden)
Section | Details
Objective | Ensure the website is functional, user-friendly, responsive, secure, and meets all design and business requirements.
Scope | Covers testing of front-end (UI/UX), back-end (functional), responsiveness, cross-browser compatibility, performance, accessibility, and security.
Out of Scope | Third-party plugins/services outside development control.

## Test Items (hidden)
Test Items
Navigation menus
Homepage and subpages
Contact forms
Authentication (Login/Signup)
Search functionality
Shopping cart/checkout (if applicable)
CMS/Admin panel
External integrations (e.g., payment gateway, maps, social media)

## Testing Types (hidden)
Test Type | Description
Functional Testing | Verify features work per requirements
Usability Testing | Ensure intuitive layout and smooth user experience
Responsive Testing | Confirm layout adapts to all screen sizes
Cross-browser Testing | Check compatibility with Chrome, Firefox, Safari, Edge
Accessibility Testing | WCAG compliance using tools like WAVE or Axe
Performance Testing | Page load speed and stress testing
Security Testing | Basic vulnerability checks (e.g., form validation, HTTPS)

## Test Environment (hidden)
Category | Details
Devices | Desktop, tablet, mobile
Browsers | Chrome, Firefox, Safari, Edge (latest versions)
Operating Systems | Windows, macOS, iOS, Android
Staging URL | https://staging.example.com

## Roles & Responsibilities (hidden)
Role | Responsibility
QA Tester | Execute tests and log bugs
Dev Team | Fix bugs and retest
Project Lead | Prioritize test coverage

## Deliverables (hidden)
Test Deliverables
Test Cases
Bug Reports
Test Summary Report
Final Sign-off Document

## Criteria (hidden)
Type | Criteria
Entry Criteria | Website features deployed to staging; Basic unit testing completed
Exit Criteria | All major bugs fixed; Critical paths tested and passed; Client approval for deployment

## Schedule (hidden)
Task | Start Date | End Date
Test Case Development | Apr 1 | Apr 3
Functional Testing | Apr 4 | Apr 6
Responsive Testing | Apr 7 | Apr 8
Cross-browser Testing | Apr 9 | Apr 10
Final Review & Sign-off | Apr 11 | Apr 12

## Sheet1
File Name: | [8 empty] | Date:
Page Title: | [8 empty] | Tester:
Browser Compatibility
| 1366x768 | 1920x1080 | 1440x900 | Other | PC | Mac | Linux | Images Disabled | CSS Disabled | Other | Notes
Internet Explorer
Microsoft Edge
Firefox
Safari
Opera
Chrome
Tablet
Smart Phone 1
Smart Phone 2
Document Validation | [5 empty] | Search Engine Optimization
| Pass | Fail | Notes |  |  |  |  | Notes
HTML Validation | [5 empty] | Meta Tag
CSS Validation | [5 empty] | Keywords in Page Title
Check Spelling | [5 empty] | Keywords in Heading
Check for Required Graphic | [5 empty] | Keywords in Content
Check for Required Content | [5 empty] | Other
Check alt Attributes | [5 empty] | Download Time Check
Test Hyperlinks | [7 empty] | Time | Notes
Accessibility Testing | [5 empty] | 56.6 kbps
Form Processing | [5 empty] | 128 kbps
Scripting/Dynamic Effects | [5 empty] | 512 kbps
Usability Testing | [5 empty] | T1 / DS1 (1.544 mbps)
Other | [5 empty] | Other
Notes

## Sheet1 (2)
File Name: | [8 empty] | Date: | 2025-04-01
Page Title: | [8 empty] | Tester: | SSG Caleb Rogers
Browser Compatibility
| 1366x768 | 1920x1080 | 1440x900 | Other | PC | Mac | Linux | Images Disabled | CSS Disabled | Other | Notes
Internet Explorer | Pass | Pass | Pass |  | Pass
Microsoft Edge | Pass | Pass | Pass |  | Pass
Firefox | Pass | Pass | Pass |  |  |  | Pass
Safari | Pass | Pass | Pass | Pass |  | Pass
Opera
Chrome | Pass | Pass | Pass | Pass | Pass
Tablet
Smart Phone 1
Smart Phone 2
Document Validation | [5 empty] | Search Engine Optimization
| Pass | Fail | Notes |  |  |  |  | Notes
HTML Validation | [5 empty] | Meta Tag
CSS Validation | [5 empty] | Keywords in Page Title
Check Spelling | 1 |  |  |  |  | Keywords in Heading
Check for Required Graphic | 1 |  |  |  |  | Keywords in Content
Check for Required Content | 1 |  |  |  |  | Other
Check alt Attributes | [5 empty] | Download Time Check
Test Hyperlinks | 1 | [6 empty] | Time | Notes
Accessibility Testing | [5 empty] | 56.6 kbps
Form Processing | [5 empty] | 128 kbps
Scripting/Dynamic Effects | [5 empty] | 512 kbps
Usability Testing | [5 empty] | T1 / DS1 (1.544 mbps)
Other | [5 empty] | Other
Notes